## Ark1
Lofthus frukt og saft |  | Team: |  | Tor-Eric, Silje, Mattis, Lars, Julie
Task |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | WEEK 7
Date | Assigned to | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06
Planning | bar: 2020-02-01 to 2020-02-09
Client meeting | Project manager | bar: 2020-02-01
Market research | Market research team | bar: 2020-02-02 to 2020-02-04
Content planning | Designer | bar: 2020-02-04 to 2020-02-06
Sitemap | Back-end developer | bar: 2020-02-06; 2020-02-08 to 2020-02-09
Design | bar: 2020-02-09 to 2020-02-21
Design plan meeting | Project manager | bar: 2020-02-09
Style tiles | Front-end developer | bar: 2020-02-10 to 2020-02-13
Visual design concepts | Front-end developer | bar: 2020-02-15 to 2020-02-20
Build | bar: 2020-02-19 to 2020-03-05
Client approval meeting | Project manager | bar: 2020-02-19
HTML & CSS | Front-end developer | bar: 2020-02-20; 2020-02-22 to 2020-02-26
Javascript | Front-end developer | bar: 2020-02-25 to 2020-02-27; 2020-02-29 to 2020-03-02
Finising the site | Project manager, front-end developer, back-end developer, designer | bar: 2020-03-03 to 2020-03-05
Launch | bar: 2020-03-05 to 2020-03-06
Launch meeting | Project manager | bar: 2020-03-05
Cross platform testing | Front-end developer | bar: 2020-03-06
UX/UI testing | Front-end developer
Refinement | Project manager, front-end developer, back-end developer, designer
Bug fixes | Back-end developer
Launch | Project manager, front-end developer, back-end developer, designer